## Sheet1
Red text: not in my hands |  | 2018 | [7 empty] | 2019 | [11 empty] | 2020 | [11 empty] | 2021 | [11 empty] | 2022
|  | Spr | Summer |  |  | Fall |  |  |  | Win | Spring |  |  |  | S |  |  | Fall |  |  |  | W | Spring |  |  |  | Summer |  |  | Fall |  |  |  | W | Spring |  |  |  | Summer |  |  | Fall |  |  |  | W | Spring |  |  |  | Summer |  |  | Fall |  |  |  | W
|  | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
Dissertation | Chapter 1
[5 empty] | Feedback | [7 empty] | Done |  |  |  | Done |  |  | Done
2nd draft
FB
3rd draft
Done
| Chapter 2 | Summer Aug: Draft Ch. 2
[9 empty] | Feedback |  |  | 2nd draft
FB
3rd draft
[17 empty] | Done |  |  | Done
| Chapter 3 | Spring Feb: Draft Ch. 3; S Jul: Draft
[18 empty] | Feedback |  |  | Feedback
2nd draft
FB
3rd draft
Done
| Chapter 4 | Fall Sep: Draft Ch. 4; Fall Nov: Done
| Revise & defend | W Jan: Revise, draft intro
Revise 3, defend
PhD, zzz
TA/GA, etc. | Teaching | Fall Sep: ENGL297; Spring Feb: Teaching / GA; S Jul: English
| GA | Fall Sep: GA Melanie Kill; S Jul: Archival; Fall Sep: Mellon/ACLS; Spring Feb: Mellon/ACLS
| Fellowship | Fall Sep: Jack Bryer; Spring Feb: Jack Bryer; S Jul: Research
Articles & chapters | Profession | Summer Jun: Kellie
Review
Revise, submit
Editorial
Edit
| OUP: ED chapter | S Jul: Draft
Review
Revise
| Reception: Dickinson fandom | S Aug: Review
Rev, resub
Accept/reject or final edit
| Women's studies | W Jan: Write; Spring Feb: Write
Review
Edit
Copyedit, due 9/1
| RSS book | Summer Aug: Under review by press
Remaining chapters
Under review
Edit
Editorial
Re-edit?
Dickinson Electronic Archives
Review
Revise
Editorial
| Douglass and Higginson: J19 | Spring Apr: Write / submit
Review
Revise
| Whitman: WWQR or American Literature | Summer Jun: Write / submit
Review
Revise
| Lind and Webster: PMLA | Fall Dec: Write / submit
Review
Revise
| Article: ("thin" geog & improv?) | Summer Jun: Write / submit
Review
Revise
Book proposals | U of GA Press | Fall Oct: Plan; Fall Dec: Prep event; Spring May: Apply; Fall Oct: Plan; Fall Dec: Prep event; Summer Jul: by 8/1
| Edinburgh | W Jan: Retreat; Spring May: by 6/1
| 33.3333 | Summer Jun: due 7/1
Conferences | MLA | W Jan: Sea; W Jan: MLA; W Jan: MLA
| ALA | Spring Mar: ALA 5/23--26; Spring Apr: ALA West
| EDIS | S Jun: EDIS: 8/8-11; Summer Jul: EDIS; Summer Jul: EDIS
| RSS | Fall Sep: RSS?
| NEMLA | Spring Feb: NEMLA; Spring Feb: NEMLA: 3/5-8
| C19 | Spring Mar: C19: 4/2-5; Fall Oct: C19: resched 10/2020
Other 1
Other 2
ECASECS | bar: Fall Sep; Fall Sep; Fall Sep; Fall Sep; Fall Sep
Other 1
Other 2
Other | Funding / job | Fall Dec: Summer funding; S Jun: prep; Fall Sep: Apply academia; Spring Feb: Apply non-academic
[8 empty] | Diss fellowships | [6 empty] | acad |  |  | Prep fellowships |  |  | Interview academia |  |  |  |  | Interview non-acad
Deadlines, commitments, & constraints:
MNS away 12/10 & 12/18-20
ST away 12/23-1/3
OUP 12/31
Lehman 1/2-1/7
MLA 1/8-1/12